## WBS-hackathon
[6 empty] | Done | In-process | Overdue
| # | Milestone | Group/Category | Stage | Task List | PIC |  |  | PLAN |  |  |  |  | ACTUAL
[7 empty] | Estimate (Minutes) | Duration (day) | Start Date | End Date | Start Date | End Date | % | Status | Duration (day) | Effort (Minutes) | Note
| Milestone 0 | Preparation | (27/10)
1 | 1.1 | Milestone 0 | Common | Access Enviroment | Identify use cases, personas, and key functions | ALL | 20 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 5
2 | 1.2 | Milestone 0 | Common | Access Enviroment | Define stack and Tools list | ALL | 20 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 5
3 | 1.3 | Milestone 0 | Common | Access Enviroment | Project Initialization & directory Structure | ALL | 20 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 5
4 | 1.4 | Milestone 0 | Common | Access Enviroment | Install packages | ALL | 20 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 10
5 | 1.5 | Milestone 0 | Prepare | WBS | Create WBS | VAN | 180 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 40
6 | 1.6 | Milestone 0 | Prepare | Rule for coding | Define checklist review code | ALL | 30 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 10
7 | 1.7 | Milestone 0 | Prepare | Rule for coding | Define Git rule | ALL | 10 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 5
8 | 1.8 | Milestone 0 | Prepare | Report | Create Milestone/report template | VAN | 60 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 10
9 | 1.9 | Milestone 0 | Prepare | AI tool | Understanding How to prompt on AI tool | ALL | 30 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 10
10 | 1.10 | Milestone 0 | Prepare | Research | Research Documents & Testcase | ALL | 60 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 20
11 | 1.11 | Milestone 0 | Prepare | Evaluate | Pick up Testcase | ALL | 20 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 5
| Milestone 1 | Front-end Development
|  | (27~ 31/10) | Demo on 30/10
1 | 2.1 | Milestone 1 | Fontend | Preparation | Define layout, color and function | ALL | 20 | 1 | 27/10 | 27/10 | 27/10 | 27/10 | 100% | Done | 1 | 15
2 | 2.2 | Milestone 1 | Fontend | Preparation | Design system architecture, high-level architecture and EDR | ALL | 30 | 1 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 100% | Done | 1 | 10
3 | 2.3 | Milestone 1 | Fontend | Preparation | Create code convention | KHOI | 15 | 1 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 100% | Done | 1 | 5
4 | 2.4 | Milestone 1 | UI/UX | Design | Design UI/UX for layout, theme, color and user experiences | KHOI | 60 | 1 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 2025-10-28 | 100% | Done | 1 | 30
5 | 2.13 | Milestone 1 | Fontend | Development | Authentication features | KHOI | 120 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-28 | 100% | Done | 1 | 30
6 |  | Milestone 1 | Fontend | Development | Common Feature | KHOI | 180 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 45
7 | 2.7 | Milestone 1 | Fontend | Development | User Management Feature | KHOI | 180 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-30 | 100% | Done | 3 | 55
8 | 2.8 | Milestone 1 | Fontend | Development | Booking management | KHOI | 120 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 30
9 | 2.9 | Milestone 1 | Fontend | Development | Comment & Review management | KHOI | 120 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-30 | 100% | Done | 3 | 45
10 | 2.10 | Milestone 1 | Fontend | Development | Payment function | KHOI | 240 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-30 | 100% | Done | 3 | 50
11 | 2.11 | Milestone 1 | Fontend | Development | Multilingual function | KHOI | 90 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 35
12 | 2.12 | Milestone 1 | Fontend | Development | Chat bot Function | KHOI | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-30 | 100% | Done | 3 | 30
13 | 2.13 | Milestone 1 | Fontend | Development | Responsive Design | KHOI | 120 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 55
14 | 2.14 | Milestone 1 | Test | Testing | Create Testcase | KHOI | 120 | 1 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 100% | Done | 1 | 30
15 | 2.15 | Milestone 1 | Test | Testing | Unit Test & Integration Test | KHOI | 90 | 1 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 100% | Done | 1 | 20
| Milestone 2 | Backend Development
|  | (28 ~ 30/10) | Demo on 30/10
1 | 2.16 | Milestone 2 | Data | Preparation | Set up Database Connection | QUY | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 15
2 | 2.17 | Milestone 2 | Data | Database | Building data models (Models) | QUY | 120 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 20
3 | 2.18 | Milestone 2 | Backend | Development | Register/login, password hash, auth middleware, admin & user | QUY | 180 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 55
4 | 2.19 | Milestone 2 | Backend | Development | Set up & Integration service API | QUY | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 35
5 | 2.20 | Milestone 2 | Backend | Development | Set up & Integration booking API | QUY | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 30
6 | 2.21 | Milestone 2 | Backend | Development | Set up & Integration branch API | QUY | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 20
7 | 2.22 | Milestone 2 | Backend | Development | Set up & Integration API Blog | QUY | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 25
8 | 2.23 | Milestone 2 | Backend | Development | Set up & Integration Feedback API | QUY | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 30
9 | 2.24 | Milestone 2 | Backend | Development | Set up & Integration Chatbot Support API | QUY | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 27
10 | 2.25 | Milestone 2 | Backend | Development | Set up & Integration Stripe API | QUY | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 45
11 | 2.26 | Milestone 2 | Backend | Development | Set up & Integration User Management API | QUY | 60 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 40
12 | 2.27 | Milestone 2 | Backend | Development | Log request & response | QUY | 120 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-30 | 100% | Done | 3 | 50
13 | 2.28 | Milestone 2 | Backend | Development | Create API documentation | QUY | 120 | 3 | 2025-10-28 | 2025-10-30 | 2025-10-28 | 2025-10-29 | 100% | Done | 2 | 10
14 | 2.29 | Milestone 2 | Backend | Development | Merge system | QUY | 240 | 1 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 100% | Done | 1 | 40
| Milestone 3 | Testing & Deployment
|  | (30 ~ 31/10) | Review on 31/10
1 | 3.1 | Milestone 3 | Test | Create | Create Testcase | ALL | 120 | 2 | 2025-10-30 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 100% | Done | 2 | 20
2 | 3.2 | Milestone 3 | Test | Testing | Unit Test & Integration Test | ALL | 180 | 2 | 2025-10-30 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 100% | Done | 2 | 40
3 | 3.3 | Milestone 3 | Test | Testing | Sytem Test | ALL | 90 | 2 | 2025-10-30 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 100% | Done | 2 | 30
4 | 3.4 | Milestone 3 | Dev | Maintance & optimize | Maintance & optimize | ALL | 180 | 2 | 2025-10-30 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 100% | Done | 2 | 30
5 | 3.5 | Milestone 3 | DevOps | Deployment | Dockerfile & docker-compose backend | QUY | 120 | 2 | 2025-10-30 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 100% | Done | 2 | 30
6 | 3.6 | Milestone 3 | DevOps | Deployment | Reverse proxy | QUY | 60 | 2 | 2025-10-30 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 100% | Done | 2 | 35
7 | 3.7 | Milestone 3 | DevOps | Deployment | Database management | QUY | 60 | 2 | 2025-10-30 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 100% | Done | 2 | 20
| Milestone 4 | Documents
|  | (30 ~ 31/10) | Review on 31/10
1 | 4.1 | Milestone 4 | Common | Sumary report | Create summary report | VANNH | 180 | 2 | 2025-10-30 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 100% | Done | 2 | 50
2 | 4.2 | Milestone 4 | Common | Sumary report | Review summary report | VANNH | 30 | 2 | 2025-10-30 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 100% | Done | 2 | 10
3 | 4.3 | Milestone 4 | Common | Demo & Evaluate | Internal review/demo | VANNH | 60 | 1 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 100% | Done | 1 | 20
4 | 4.4 | Milestone 4 | Common | Demo & Evaluate | Review & Assessment | VANNH | 60 | 1 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 100% | Done | 1 | 15
[15 empty] | Effort estimate | 4495 | 0.30078
[15 empty] | Real Effort | 1352